## 3-30-22
Enter Project # and Name
PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2021-11-29 | Project Setup | 0 | 0 | 25 | 2021-11-29 | Project Setup
2021-12-05 | Construction Document Development Phase | 0 | 0 | 5 | 2021-12-05 | Construction Document Development Phase
2021-12-10 | Construction Document Completion | 0 | 0 | -5 | 2021-12-10 | Construction Document Completion
2021-12-22 | Construction Bids Received | 0 | 0 | 30 | 2021-12-22 | Construction Bids Received
2022-03-22 | Notice to Proceed | 0 | 0 | -20 | 2022-02-16 | Notice to Proceed
2022-03-24 | Pre-Construction Meeting | 0 | 0 | 15 | 2022-02-18 | Pre-Construction Meeting
31-Aug- | Substantial Completion | 0 | 0 | -15 | 2022-08-18 | Substantial Completion
2022-09-01 | Warranty Period | 0 | 0 | 15 | 2022-09-01 | Warranty Period
2022-09-18 | Project End | 0 | 0 | -20 | 2022-09-30 | Project End
|  | 0 |  | 5 | #NAME?
|  | 0 |  | 5 | #NAME?
|  | 0 |  | 5 | #NAME?

## Project Timeline
4317 Veterans Housing Improvements Phase II
PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2021-11-29 | Project Setup | 25 | 0 | 25 | 2021-11-29 | Project Setup
2021-12-05 | Construction Document Development Phase | 5 | 0 | 5 | 2021-12-05 | Construction Document Development Phase
2021-12-10 | Construction Document Completion | -5 | 0 | -5 | 2021-12-10 | Construction Document Completion
2021-12-22 | Construction Bids Received | 30 | 0 | 30 | 2021-12-22 | Construction Bids Received
2022-02-16 | Notice to Proceed | -20 | 0 | -20 | 2022-02-16 | Notice to Proceed
2022-02-18 | Pre-Construction Meeting | 15 | 0 | 15 | 2022-02-18 | Pre-Construction Meeting
2022-08-18 | Substantial Completion | -15 | 0 | -15 | 2022-08-18 | Substantial Completion
2022-09-01 | Warranty Period | 15 | 0 | 15 | 2022-09-01 | Warranty Period
2022-09-30 | Project End | -20 | 0 | -20 | 2022-09-30 | Project End
|  | 0 |  | 5 | #NAME?
|  | 0 |  | 5 | #NAME?
|  | 0 |  | 5 | #NAME?

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 6 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 14 | 9 | 1 | 2021-11-29 | Project Setup | 25 | 8 | 9 | 2021-11-29 | Project Setup | 25
|  |  | 8 | 2 | 2021-12-05 | Construction Document Development Phase | 5 | 7 | 8 | 2021-12-05 | Construction Document Development Phase | 5
|  |  | 7 | 3 | 2021-12-10 | Construction Document Completion | -5 | 6 | 7 | 2021-12-10 | Construction Document Completion | -5
|  |  | 6 | 4 | 2021-12-22 | Construction Bids Received | 30 | 5 | 6 | 2021-12-22 | Construction Bids Received | 30
|  |  | 5 | 5 | 2022-02-16 | Notice to Proceed | -20 | 4 | 5 | 2022-02-16 | Notice to Proceed | -20
|  |  | 4 | 6 | 2022-02-18 | Pre-Construction Meeting | 15 | 3 | 4 | 2022-02-18 | Pre-Construction Meeting | 15
|  |  | 3 | 7 | 2022-08-18 | Substantial Completion | -15 | 2 | 3 | 2022-08-18 | Substantial Completion | -15
|  |  | 2 | 8 | 2022-09-01 | Warranty Period | 15 | 1 | 2 | 2022-09-01 | Warranty Period | 15
|  |  | 1 | 9 | 2022-09-30 | Project End | -20 | 0 | 1 | 2022-09-30 | Project End | -20